## Sheet1
Google Summer of Code 2015 – FOSSASIA - sQuick

DATE	DAY	ACTIVITY/TASK COMPLETED	MEETING HELD	MEETING WITH	Extra Stuff

31/05/15	Sunday	Started UI development	No
01/06/15	Monday	Started UI, Wrote GDG I/O Blog	Yes	Martin
02/06/15	Tuesday	File Access done. Addition of Drop Down Menu + Help Text + Color Change.	Yes	Martin, Sean (later)
03/06/15	Wednesday	Explore file access & Discuss ideas about GUI	Yes	Martin, Sean
04/06/15	Thursday	Make metacello configuration + Configuration Browser for easy code loading	Yes	Martin, Sean
05/06/15	Friday	Content window added, Instance Cache removed	Yes	Martin
06/06/15	Saturday	New mock-up designed + Blog published	-	-
07/06/15	Sunday	Explored Stuff	-	-
08/06/15	Monday	Project Report mailed	Yes	Martin, Sean
09/06/15	Tuesday	Made sQuick_new	Yes	Martin
10/06/15	Wednesday	Designed new Mock-ups	Yes	Martin, Sean
11/06/15	Thursday	Designed GUI using Spec	Yes	Martin	https://www.youtube.com/watch?v=OL23s9ZUIR0&index=13&list=PL4actYd6bfnz98ngrKALwwStl3C3odEKG
12/06/15	Friday	Explored existing search package, discussion with Max, Published Project Apprise on Blog	Yes	Martin, Sean
13/06/15	Saturday	OFF	-	-
14/06/15	Sunday	OFF	-	-
15/06/15	Monday	Image re-scaling, sQuick_new configuration	Yes	Martin, Sean
16/06/15	Tuesday	Morph re-positioning, Back button implementation	Yes	Martin, Sean
17/06/15	Wednesday	Improvised GUI, cleaned up code	Yes	Martin
18/06/15	Thursday	Explored text search package, Dictionary subclass for index implementation	Yes	Martin, Sean
19/06/15	Friday	Try Dummy Index	Yes	Martin, Sean
20/06/15	Saturday	Push Dummy Index code to github	Yes	Martin
21/06/15	Sunday	OFF	No	-
22/06/15	Monday	Indexing Documents, Test Run successful	Yes	Martin
23/06/15	Tuesday	Indexing of all files together	Yes	Martin
24/06/15	Wednesday	Search Assesrtion Works	Yes	Martin
25/06/15	Thursday	User Input retreival successful	Yes	Martin
26/06/15	Friday	MID TERM EVALUATION Starts	Yes	Martin
27/06/15	Saturday	-	-	-
28/06/15	Sunday	-	-	-
29/06/15	Monday	Fetch search results as an array + Added class comments	Yes	Martin
30/06/15	Tuesday	Printed search results in PopUp
01/07/15	Wednesday
02/07/15	Thursday
03/07/15	Friday	MID TERM EVALUATION Ends
04/07/15	Saturday
05/07/15	Sunday
06/07/15	Monday
07/07/15	Tuesday
08/07/15	Wednesday
09/07/15	Thursday
10/07/15	Friday
11/07/15	Saturday
12/07/15	Sunday
13/07/15	Monday
14/07/15	Tuesday
15/07/15	Wednesday
16/07/15	Thursday
17/07/15	Friday
18/07/15	Saturday
19/07/15	Sunday
20/07/15	Monday
21/07/15	Tuesday
22/07/15	Wednesday
23/07/15	Thursday
24/07/15	Friday
25/07/15	Saturday
26/07/15	Sunday
27/07/15	Monday
28/07/15	Tuesday
29/07/15	Wednesday
30/07/15	Thursday
31/07/15	Friday
01/08/15	Saturday
02/08/15	Sunday
03/08/15	Monday
04/08/15	Tuesday
05/08/15	Wednesday
06/08/15	Thursday
07/08/15	Friday
08/08/15	Saturday
09/08/15	Sunday
10/08/15	Monday
11/08/15	Tuesday
12/08/15	Wednesday
13/08/15	Thursday
14/08/15	Friday
15/08/15	Saturday
16/08/15	Sunday
17/08/15	Monday
18/08/15	Tuesday
19/08/15	Wednesday
20/08/15	Thursday
21/08/15	Friday
22/08/15	Saturday
23/08/15	Sunday
24/08/15	Monday
25/08/15	Tuesday
26/08/15	Wednesday
27/08/15	Thursday
28/08/15	Friday
29/08/15	Saturday
30/08/15	Sunday
31/08/15	Monday
01/09/15	Tuesday